OPERATING SYSTEM

Fit Call and Workflow Diagnostic

Artefact register, stage gates and operating map

| Owner | Heutrix Pty Ltd ¦ accountable roles to be ratified |
| --- | --- |
| Version | 1.0 ¦ 1 August 2026 |
| Offer | One-workflow Workflow Diagnostic ¦ AUD 950 plus GST |
| Status | Operational draft ¦ legal pack stop-issue items still apply |

Use rule: Start with the free fit call. Offer the paid Diagnostic only when one workflow can be defined, the client can work with non-identifying evidence, and the expected outcome matches the signed Order Form.

Legal readiness: The existing Client Legal Pack is a first draft for solicitor review. Verify the entity, ABN/GST, insurance, addresses, approved systems, privacy contacts and signing authority before first client issue.

# 1. Pack contents

| ID | Artefact | Class | Purpose |
| --- | --- | --- | --- |
| 00 | Artefact Register | Internal | Shows which artefact is used at each stage and the minimum control gates. |
| 01 | Fit Call Playbook and Scripts | Internal | Runs the 30-minute call, qualifies fit and records the decision. |
| 02 | Workflow Diagnostic Delivery Playbook | Internal | End-to-end SOP from signed order through acceptance and secure closeout. |
| 03 | Client Forms and Communications | Controlled template | Reusable intake, preparation and email templates. |
| 04 | Findings Report Template | Client confidential | Editable report structure aligned to the contracted deliverables. |
| 05 | Diagnostic Working Workbook | Internal / client confidential | Qualification, evidence, process, analysis, opportunity and QA registers. |
| 06 | Workflow Maps and Findings Deck | Client confidential | Editable current-state, future-state and presentation template. |

# 2. Existing legal artefacts used with this pack

Before exchanging non-public information. Use the Mutual Confidentiality Agreement where required. Do not invite sensitive information into a fit call.

Every paid Diagnostic. Issue and sign the Client Services Agreement plus the Workflow Diagnostic Order Form before work starts.

Any protected data or system access. Complete Data and System Access Authorisation before access is granted. The Diagnostic default remains no Personal Information or sensitive information.

Any AI use. Complete the AI Use Case Approval for one tool and one use case. No client data is approved for AI by silence.

Any scope, fee, timing, tool or data change. Use the Change Request before the changed work proceeds.

Acceptance and close. Use Deliverable Review and Acceptance, then Handover and Access Closure.

# 3. End-to-end operating map

| Stage | Name | Work | Output | Gate |
| --- | --- | --- | --- | --- |
| 0 | Enquiry | Non-identifying problem description | Fit call booked or declined | No sensitive information received |
| 1 | Fit call | 30-minute structured call | Proceed / clarify / do not proceed | One workflow and safe data path defined |
| 2 | Commercial activation | CSA + Order Form + payment | Project authorised | Signed contract and cleared payment |
| 3 | Kickoff and evidence | Scope, data check, max 5 documents / 50 pages | Workshop-ready evidence set | Owner, attendees, dates and repository confirmed |
| 4 | Discovery workshop | Up to 90 minutes / up to 4 participants | Validated current-state capture | Start/end, roles, steps, decisions and exceptions recorded |
| 5 | Analysis and design | Map, root-cause and opportunity analysis | Draft deliverable set | Facts, assumptions and recommendations separated |
| 6 | Internal QA | Independent review where practical | Client-ready draft | Scope, privacy, logic and acceptance checks pass |
| 7 | Findings presentation | Up to 60 minutes | Questions, decisions and corrections logged | Material questions recorded |
| 8 | Acceptance and closeout | Five-day review + one correction round | Accepted and securely closed | Access removed and data disposition recorded |

# 4. Control points that cannot be skipped

| [ ] | Fit call notes contain no patient, participant, worker or other sensitive identifying information. |
| --- | --- |
| [ ] | The workflow is one operational workflow with an agreed start and end. |
| [ ] | The client understands the Diagnostic is evidence-led advice, not implementation, assurance or an audit. |
| [ ] | The Client Services Agreement and Workflow Diagnostic Order Form are signed before paid work starts. |
| [ ] | Payment and the agreed inputs are received before the delivery clock starts. |
| [ ] | Only the approved repository and approved named users are used. |
| [ ] | AI is not used with client confidential information or client data without a signed AI Use Case Approval. |
| [ ] | Every finding is traceable to evidence, an observation or an explicitly labelled assumption. |
| [ ] | The report, maps, opportunity list and presentation tell the same story. |
| [ ] | Acceptance, handover, access removal and data return/deletion are recorded at close. |

# 5. Role model

Governance gap: Named founder assignments in the current planning notes are recommendations, not ratified appointments. Use the functional roles below until Heutrix formally assigns named owners.

| Role | Accountability |
| --- | --- |
| Commercial Lead | Owns enquiry, fit decision, offer accuracy, client identity and contract issue. |
| Engagement Lead | Accountable for scope, workshop, analysis, deliverables, client communication and schedule. |
| Facilitator | Runs the workshop, keeps scope narrow and draws out workflow evidence. |
| Analyst | Maintains working papers, maps, findings, opportunity scores and decision trail. |
| Quality Reviewer | Challenges scope drift, unsupported claims, map consistency and acceptance readiness. |
| Privacy / Security Reviewer | Approves data, repository, access and any AI exception before use. |
| Client Project Owner | Confirms facts, consolidates feedback, coordinates attendees and accepts deliverables. |

# 6. File and record structure

- Use a project ID in the form HTX-WD-[YYYY]-[NNN]-[CLIENT SHORT NAME].

- Keep 01 Contract, 02 Client Inputs, 03 Working Papers, 04 Draft Deliverables, 05 Issued Deliverables and 06 Closeout as separate folders in the approved repository.

- Use ISO dates in file names: YYYY-MM-DD. Use version labels v0.1, v0.2 for drafts and v1.0 for the accepted issue.

- Never store credentials, unapproved personal information or raw recordings in the project folder.

- Keep one evidence register and one decision log as the source of truth; do not create competing copies in email and personal notes.

# 7. Definition of done

| [ ] | All contracted deliverables exist in editable and agreed issue formats. |
| --- | --- |
| [ ] | The current-state map covers the agreed start/end, roles, handovers, decisions and known pain points. |
| [ ] | The future-state map shows recommended ownership, controls and material changes. |
| [ ] | The opportunity list is prioritised with rationale, dependencies and a high-level implementation option. |
| [ ] | The report distinguishes evidence, assumptions and recommendations. |
| [ ] | The findings session is completed and material questions are recorded. |
| [ ] | The consolidated correction round is completed or formally waived. |
| [ ] | Deliverable review, handover, access closure and data disposition are recorded. |

## Source alignment

This artefact is aligned to the Heutrix Instructions, Voice and Notes dated 31 July 2026; the Heutrix Client Services Agreement v1.0; the Workflow Diagnostic Order Form v1.0; and the Project Control Forms v1.0. If a signed client document differs, the signed document controls.